## Lekha's Team
SI No | Date | Sprint | Ticket No | Task Type | Description | Client Name | Detailed task description | Total Hours spent | Hours spent in details | stake holder | Team Member | Team Lead | Current status
1 | 13/04/2020 |  |  | Adhoc | Configuring Desktop Setup with IT Team |  | Had a call with IT Team taken remote control | 3hours |  |  | Irfan | Shimith
2 | 13/04/2020 |  | 33148 | Assigned | Salary Certificate | British Council | Bulk Download of Salary Certificate | 4hours |  | Vinod | Irfan | Shimith | pending
3 | 13/04/2020 |  |  | Assigned | Going through the flow of the modules |  | Going through the workflow of the Modules from frontend | 1hour |  |  | Irfan | Shimith
4 | 14/04/2020 |  |  | Assigned | Analyzing the code of TA modules |  | Analyzing the code of TA module | 4hours |  |  | Irfan | Shimith
5 | 14/04/2020 |  |  | Adhoc | Contact with IT Team |  | Connectivity issues | 3hours |  |  | Irfan | Shimith
6 | 14/04/2020 |  |  | Assigned | Analyzing the code of TA modules |  | Analyzing the code of TA module | 1hour |  |  | Irfan | Shimith
7 | 15/04/2020 |  |  | Assigned | Analyzing the code of TA modules |  | Analyzing the code of TA module | 3hours |  |  | Irfan | Shimith
8 | 15/04/2020 |  |  | Assigned | Analyzing the code the Workforce modules |  | Analyzing the code the Workforce modules | 1hour |  |  | Irfan | Shimith
9 | 15/04/2020 |  |  | Adhoc | setting up the local system setup |  | setting up the local system setup | 2hours |  |  | Irfan | Shimith
10 | 15/04/2020 |  |  | Adhoc | Contacting with IT Team |  | Contacting with IT Team for share folder access and for the local data | 2hours |  |  | Irfan | Shimith
1 | 16/04/2020 |  |  | Assigned | Process Verfication |  | Analyzing the code of TA module | 6:00 | Analyzing the code of TA module |  | Irfan | Shimith | working
2 | 16/04/2020 |  |  | Assigned | Process Verfication |  | Analyzing the code the Workforce modules | 2:00 | Analyzing the code the Workforce modules |  | Irfan | Shimith | completed
3 | 16/04/2020 |  |  | Assigned | Making one complete round of process |  | Analyzing the flow of the modules | 1:00 | Making one complete round of process as per workflow |  | Irfan | Shimith | completed
1 | 17/04/2020 |  | #42292 | Assigned | Onboarding Module | Celio Fashion | Analyzing the code fixing the issue which was raised. | 9:00 | Analyzing the code fixing the issue i.e., extra form fields where displaying while generating candidate info in pdf | Apurva | Irfan | Shimith | working
2 | 17/04/2020 |  | #42473 | Assigned | Good Hope payslip changes | Good Hope | Analyzing the requirement and Planning how to implement | 1:00 | Analyzing the code the Workforce modules | Nagesha | Irfan | Shimith | working
1 | 18/04/2020 |  | #39224 | Assigned | Income Tax Report | Good Hope | Testing the payroll Report | 1:00 | Testing the payroll Report | Nagesha | Irfan | Shimith | completed
2 | 18/04/2020 |  | #42473 | Assigned | Good Hope payslip changes | Good Hope | Making changes in the payslip as per the requirement | 7:30 | Making changes in the payslip as per the requirement | Nagesha | Irfan | Shimith | working
3 | 18/04/2020 |  | #42292 | Assigned | Onboarding | celio | Had a discussion on the form management issue | 0:45 | Had a discussion on the form management issue | Apurva | Irfan | Shimith | working
1 | 20/04/2020 |  | #39224 | Assigned | Salary Certificate | British Council | Generation Word Document and Signatory Details | 3:00 | Developing Generation Word Document and Signatory Details | Vinod | Irfan | Shimith | working
2 | 20/04/2020 |  | #33148 | Assigned | Good Hope payslip changes | Good Hope | Enhancing the payslip as per the requirement | 8:30 | Enhancing the payslip as per the requirement | Nagesha | Irfan | Shimith | working
1 | 21/04/2020 |  | #39224 | Assigned | Salary Certificate | British Council | Generation Word Document and Signatory Details | 3:00 | Developing Generation Word Document and Signatory Details | Vinod | Irfan | Shimith | working
2 | 21/04/2020 |  | #33148 | Assigned | Good Hope payslip changes | Good Hope | Enhancing the payslip as per the requirement | 8:30 | Enhancing the payslip as per the requirement | Nagesha | Irfan | Shimith | working
1 | 22/04/2020 |  | #39224 | Assigned | Salary Certificate | British Council | Generation Word Document and Signatory Details | 8:00 | Developing Generation Word Document and Signatory Details | Vinod | Irfan | Shimith | working
2 | 22/04/2020 |  | #33148 | Assigned | Good Hope payslip changes | Good Hope | Making modifcations as per the request | 1:30 | Making modifcations as per the request | Nagesha | Irfan | Shimith | working
1 | 23/04/2020 |  | #39224 | Assigned | Salary Certificate | British Council | Generation Word Document and Signatory Details | 6:00 | Developing Generation of Word Document and Signatory Details | Vinod | Irfan | Shimith | working
2 | 23/04/2020 |  | #33148 | Assigned | Good Hope payslip changes | Good Hope | Converting amount into millions and cents | 3:00 | Converting amount into millions and cents | Nagesha | Irfan | Shimith | working
1 | 24/04/2020 |  | #39224 | Assigned | Salary Certificate | British Council | Generation Word Document and Signatory Details | 2:00 | Developing Generation of Word Document and Signatory Details | Vinod | Irfan | Shimith | working
2 | 24/04/2020 |  | #33148 | Assigned | Good Hope payslip changes | Good Hope | Working as per the requirement | 5:00 | Converting amount into millions and cents | Nagesha | Irfan | Shimith | working
3 | 24/04/2020 |  |  | Adhoc | Conection issues |  | IT team fixing the issues. | 2:00 | IT team fixing the issues.
1 | 25/04/2020 |  | #39224 | Assigned | Salary Certificate | British Council | Generation Word Document and Signatory Details | 6:00 | Developing Generation of Word Document and Signatory Details | Vinod | Irfan | Shimith | Testing
2 | 25/04/2020 |  | #33148 | Assigned | Good Hope payslip changes | Good Hope | Working as per the requirement | 3:00 | Payslip changes and adding new fields in payslips | Nagesha | Irfan | Shimith | Completed
3 | 27/04/2020 |  | #39224 | Assigned | Salary Certificate | British Council | R&D ON Displaying logo in ms word through php | 9:00 | R&D ON Displaying logo in ms word through php | Vinod | Irfan | Shimith | Working
4 | 28/04/2020 |  | #39224 | Assigned | Salary Certificate | British Council | R&D ON Displaying logo in ms word through php | 6:00 | R&D ON Displaying logo in ms word through php | Vinod | Irfan | Shimith | Working
5 | 28/04/2020 |  | #42662 | Assigned | Salary Certificate | British Council | copying the functionality to employee role as well as db changes | 3:00 | copying the functionality to employee role as well as db changes | Vinod | Irfan | Shimith | Working
6 | 28/04/2020 |  |  | Meeting | Team Meeting |  | Team Meetin | 0:30 | Team Meeting on powerpay tool |  | Irfan | Shimith | Completed
7 | 29/04/2020 |  | #39224 | Assigned | Salary Certificate | British Council | R&D ON Displaying logo in ms word through php | 5:00 | R&D ON Displaying logo in ms word through php | Vinod | Irfan | Shimith | Working
8 | 29/04/2020 |  | #42662 | Assigned | Salary Certificate | British Council | copying the functionality to employee role as well as db changes | 4:00 | copying the functionality to employee role as well as db changes | Vinod | Irfan | Shimith | Working
9 | 30/04/2020 |  | #42662 | Assigned | Salary Certificate | British Council | Testing the functionality which moved to live | 3:00 | Testing the functionality which moved to live | Vinod | Irfan | Shimith | Completed
10 | 30/04/2020 |  |  | R&D | PHP WoRD |  | R&D on php word library | 4:00 | R&D on php word library |  | Irfan | Shimith | Working
11 | 30/04/2020 |  |  | Adhoc | Analyzing the code of TA Module |  | Analyzing the code of TA Module | 2:00 | Analyzing the code of TA Module |  | Irfan | Shimith | Working
12 | 2020-04-05 |  | #39224 | Assigned | Salary Certificate | British Council | R&D ON Displaying logo in ms word through php | 6:00 | R&D ON Displaying logo in ms word through php | Vinod | Irfan | Shimith | Working
13 | 2020-04-05 |  | #39224 | Adhoc | Analyzing the code of TA Module |  | Analyzing the code of TA Module | 2:00 | Analyzing the code of TA Module |  | Irfan | Shimith | Working
14 | 2020-05-05 |  | #39224 | Assigned | Salary Certificate | British Council | Changes as per the request and live updation | 10:00 | Changes as per the request and live updation | Vinod | Irfan | Shimith | Testing
15 | 2020-06-05 |  | #39224 | Assigned | Salary Certificate | British Council | Fixing the bugs which was raised while tesing in live server | 4:00 | Fixing the bugs which was raised while tesing in live server | Vinod | Irfan | Shimith | Completed
16 | 2020-06-05 |  |  | Adhoc | Analyzing the code of TA Module |  | Analyzing the code of TA Module | 3:00 | Analyzing the code of TA Module |  | Irfan | Shimith | Working
17 | 2020-06-05 |  |  | R&D | PHP WoRD libraries |  | R&D on php word library | 1:00 | R&D on php word library |  | Irfan | Shimith | Working
18 | 2020-07-05 |  |  | Adhoc | Analyzing the code of TA Module |  | Analyzing the code of TA Module | 3:00 | Analyzing the code of TA Module |  | Irfan | Shimith | Working
19 | 2020-07-05 |  |  | Adhoc | Analyzing the code of Onboarding Module |  | Analyzing the code of Onboarding Module | 4:00 | Analyzing the code of Onboarding Module |  | Irfan | Shimith | Working
20 | 2020-07-05 |  |  | R&D | PHP libraries |  | R&D on php library | 1:00 | R&D on php library |  | Irfan | Shimith | Working
21 | 2020-08-05 |  | #42891 | Assigned | login Status updation | Agile | login Status updation | 3:00 | Login Status Updation | dhananjay | Irfan | Shimith | Completed
22 | 2020-08-06 |  | #42888 | Assigned | Fixing the issue which was raised | Eurofins IT | Fixing the issue which was raised | 4:00 | Going through the code and analyzing it | prashanth | Irfan | Shimith | Completed
23 | 2020-08-07 |  |  | R&D | PHP libraries |  | R&D on php library | 1:00 | R&D on php library |  | Irfan | Shimith | Working
24 | 2020-11-05 |  |  | Adhoc | Analyzing the code of Onboarding Module |  | Analyzing the code of Onboarding Module | 4:00 | Analyzing the code of Onboarding Module |  | Irfan | Shimith | Working
25 | 2020-11-05 |  |  | Assigned | Going through the code of payroll report sp module | SLK Phillipines | Going through the code of payroll report sp module | 4:00 | Going through the code of payroll report sp module | Aditya | Irfan | Shimith | Working
26 | 2020-11-05 |  | #42948 | Assigned | Input Module acces for list of employee |  | Input Module acces for list of employee | 1:00 | Input Module acces for list of employee | Girish | Irfan | Shimith | Working
27 | 2020-12-05 |  |  | Assigned | Going through the code of payroll report sp module | SLK Phillipines | Going through the code of payroll report sp module | 4:00 | Going through the code of payroll report sp module | Aditya | Irfan | Lekha | Completed
28 | 2020-12-05 |  | #42948 | Assigned | Input Module acces for list of employee |  | Input Module acces for list of employee | 48:00 | Input Module acces for list of employee | Girish | Irfan | Lekha | Working